## Scope of Work
Project: Mathilda Ave Landscaping Project
SUBJECT: Form 10 RESOURCE PLAN (stated in percentage only)
[5 empty] | DESIGN CONSULTANTS | [8 empty] | Subconsultant Services | [6 empty] | Subconsultant Services | [6 empty] | Other Services | [6 empty] | GRAND
Item No. | Description | UNIT | Total Time |  | Principal - in Charge | Project Manager | Deputy Project Manager | Project Engineer | Associate Engineer | Assistant Engineer | Sr. Design & Tech | CADD Admin | TOTAL HRS | Project Manager | Project Engineer | Associate Engineer | Field Engineer | Lab Tech | Engineering Draft | TOTAL HRS | Project Manager | Project Engineer | Associate Engineer | Field Engineer | Lab Tech | Engineering Draft | TOTAL HRS | Project Manager | Project Engineer | Associate Project Engineer | Assistant Project Engineer | Sr. Design & Tech | TOTAL HRS |  | TOTAL HRS
PLANS, SPECIFICATIONS, & ESTIMATES (PS&E) PHASE
A. Background Information
This RFP is for performing Task 1 (Project Management) and Task 2 (35% Plans, Specifications, & Estimates (PS&E)), as outlined below, for the US 101/De La Cruz Boulevard/Trimble Road Interchange Improvement Project (“Project”). The selected Proposer providing Services for this Project may be awarded follow-on work, including Task 3 through Task 7 as described below.
B. Proposed Project
The proposed Project is located on US 101 in the City of San Jose, Santa Clara County, California. The Project limits are approximately between 0.7 mile north of De La Cruz Boulevard/Trimble Road and 0.8 mile south of De La Cruz Boulevard/Trimble Road. The proposed Project is shown in the Location Map - Appendix A.
The improvements under the Project will include reconstructing the existing three-quadrant cloverleaf interchange to a Type L-9 partial cloverleaf interchange by replacing the existing overcrossing structure across US 101 and widening of De La Cruz Boulevard/Trimble Road to six travel lanes.
The Project is Categorically Exempt (“CE”) under Class 1 of the California Environmental Quality Act (“CEQA”) guidelines. A Notice of Exemption was filled by VTA on November 21, 2013. The Project Report (“PR”) was approved on March 11, 2016, and included in Appendix B. The CE is included in Appendix B attached to the PR. Other information and reports prepared during the Project Approval/Environmental Document (“PA/ED”) phase are included in Appendix G.
Work to be performed:
The scope of the construction package consists of the following Project elements and includes, but is not limited to, the following:
1. Replace the existing De La Cruz Boulevard Bridge Overcrossing with an eight-lane facility, which includes exit lanes to the northbound and southbound loop on ramps. Replacement would use precast pre-stressed I-girders to reduce structure depth, provide standard vertical clearance over US 101 and to allow for construction under the air space restriction of the adjacent Mineta San Jose International Airport.
2. Modify existing De La Cruz Boulevard to provide an additional through lane in each direction from De La Cruz Boulevard-Seaboard Avenue to Central Expressway.
3. Reconstruct the northbound diagonal on-ramp from De La Cruz Boulevard to provide two mixed flow lanes and one preferential High Occupancy Vehicle (HOV) by-pass lane.
4. Modify the northbound loop on-ramp from De La Cruz Boulevard to provide one mixed flow lane and one preferential HOV by-pass lane.
5. Modify the southbound loop on-ramp from De La Cruz Boulevard to provide two mixed flow lanes.
6. Construct a new signalized intersection at the terminus of the US 101 southbound off-ramp at De La Cruz Boulevard.
7. Reconstruct the southbound diagonal on-ramp from De La Cruz Blvd to provide two mixed flow lanes and one preferential HOV by-pass lane.
8. Construct California Highway Patrol (“CHP”) enforcement areas on each on-ramp, including maintenance vehicle pullout areas.
9. Provide a 10 ft. wide pedestrian sidewalk on the north side of De La Cruz Boulevard between Trimble Road and Central Expressway.
10. Provide dedicated bicycle facilities serving both directions on De La Cruz Boulevard between De La Cruz Boulevard-Seaboard Avenue and Central Expressway.
11. Reconstruct the intersection of De La Cruz Boulevard and Central Expressway to provide bike lanes, and additional through and turn lanes. Provide lane transition as needed on Central Expressway.
12. Provide low height roadway and ramp safety lighting and signing in compliance with Federal Aviation Administration (“FAA”) glide slope clearance requirements.
13. Provide island and fence for a portion of the Mineta San Jose International Airport and Instrument Landing System (“ILS”) landing light system that crosses De La Cruz Boulevard.
14. Modify existing drainage systems to accommodate the interchange improvements.
15. Reconstruct all ramp metering systems that are affected by the Project’s proposed improvements.
C. Additional Project Elements
Contractor’s designs will: (i) consider an evaluation of bicycle and pedestrian access that follows the latest VTA “Complete Streets” Resolution and Policy; (ii) if necessary, develop or improve bicycle and pedestrian and transit facilities on De La Cruz Boulevard – Trimble Road and possibly surrounding areas (also see Attachment G and Page 23 and 24 of the PR for more information); and (iii) provide better connections to local roads and planned developments in the area. See Appendix C for the 2009 VTA’s adopted Multi-Modal Design Practices and Principles. Appendix D is the approved 2017 VTA Complete Streets Resolution and Policy. Contractor will assist VTA in complying with the requirements of reporting as outlined in the 2016 Measure B Complete Streets Reporting Requirements in Appendix E.
D. Proposed Scope of Work
Contractor will provide design services for the Project, including all fieldwork, investigations, special studies and preparation of construction documents ready for bidding. Contractor will perform all Services in accordance with the standards outlined below:
Applicable Standards
The documents, reports, plans, specifications and estimates (“PS&E”) will be prepared in accordance with Caltrans' regulations, policies, procedures, manuals and standards, including compliance with Federal Highway Administration (“FHWA”) and FAA requirements. The standards described below in A through K are not all-inclusive, but are intended only to illustrate types of sources.
A. Roadway design must be in accordance with the latest editions, if applicable, of the Caltrans Highway Design Manual, the English Highway Design Standards, and the California Manual on Uniform Traffic Control Devices (CA MUTCD). The current editions of those manuals are: Caltrans Highway Design Standards 2016 Standards for English Plans, the 2015 English Standard Specification, and the 2014 California Manual on Uniform Traffic Control Devices (“CA MUTCD”) and VTA standards.
B. Plans must be prepared in conformance with the latest editions of the Caltrans Drafting and Plans Manual and the Caltrans CADD User’s Manual.
C. Plans, specifications, and estimates must be prepared in conformance with the latest editions of the Caltrans Plans, Specifications and Estimates Guide.
D. All field and laboratory testing for geotechnical investigations must be performed and the Materials Report will be prepared in conformance with current editions of the Guidelines for Geotechnical Design Reports.
E. Bridge plans, specifications, estimate and calculations must be in accordance with the Caltrans Division of Structures (“DOS”) Bridge Design Details Manual, Bridge Design Aids Manual, Bridge Memos to Designers, Bridge Design Specifications, Improved Seismic Design Criteria for California Bridges, and the latest Seismic Design Criteria (“SDC”).
F. All surveys must conform to the current Caltrans Surveys Manual. Horizontal datum to be CCS 83, Epoch 2010.00 (California Coordinate System, North America Datum, 1983) and vertical datum to be NAVD 88 (North American Vertical Datum of 1988).
G. Design of improvements which impact existing or proposed underground utilities must conform to Caltrans Policy on High and Low Risk Underground Facilities Within Highway Right-of-Way.
H. All right-of-way maps must conform to the current Caltrans Right-of-Way Manual. Design of the Project must be performed in accordance with Caltrans standards and practices. Any exceptions to applicable design standards must be approved by Caltrans via the process outlined in Caltrans Highway Design Manual and applicable memorandums and design bulletins published by Caltrans.
I. All designs for the constructed improvements within the City of San Jose and the City of Santa Clara (collectively referred to as “City”) right-of-way must conform to the City of San Jose and City of Santa Clara Standard Plans, Guidelines, Policy and Procedure, and City Ordinances.
J. All designs for the constructed improvements must conform to FAA and Mineta San Jose International Airport requirements.
K. All constructed improvements will be required to conform to Complete Streets best practices in order to improve bicycle, pedestrian, and transit elements of the system. Design of bicycle improvements must comply with most recent version of VTA Bicycle Technical Guidelines (“BTG”).
Contractor will complete the following two PS&E phase Tasks:
TASK 1.Project Management
TASK 2. Preliminary Engineering (35% PS&E)
VTA may, in its sole discretion, authorize Contractor to perform the following Tasks by a written Contract amendment:
TASK 3.Final Design - Unchecked (65% PS&E)
TASK 4. Final Design - Checked (95% PS&E)
TASK 5. Final Design (100% PS&E) and (Final PS&E)
TASK 6. Construction Bidding Services
TASK 7. Design Support During Construction
TASK 1: PROJECT MANAGEMENT
1.1-1.3 | Project Administration/Project Coordination | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.4 | Maintain Project files | HRS | 0 | [16 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.5 | No Extra Work Without VTA Authorization | N/A
1.6 | Prepare Documents | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.7 | Attend PDT Meeting and Coordination | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.8 | Prepare and Update CPM | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.9 | Attend PDT Meeting and Coordination | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.1 | Prepare and Submit Monthly Budgets, Invoices and Progress Report | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.11 | Prepare and Submit Correspondence, Memos and Meeting Minutes | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.12 | Establish and Implement QC/QA Procedures | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
1.13 | Conduct PDT Trend Meetings and Prepare Minutes (Task 1.9) | N/A
| Sub Total: TASK 1 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 2: PLANNING AND PRELIMNARY INVESTIGATIONS\
2.1 | Data Collection and Review | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
2.2 | Topographic Mapping and Existing CAD Files | N/A
2.3 | Design Development Inventory, Analysis and Modeling | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
2.4 | Final Design Development | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
2.5 | Coordination with Others | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
2.6 | Design Surveys | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
2.7 | Project Development Team Meeting (Task 1.9) | N/A
| Sub Total: TASK 2 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 3. PRELIMINARY DESIGN - (35% PS&E) | [12 empty] | 0
3.1 | Highway Planting Plan Sheets | HRS | 0 | [31 empty] | 0
3.2 | Design Workshops with Caltrans and City | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 | #REF! | 0
3.3 | Draft Design Reports | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
3.4 | High-Low Risk Utility Certification | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
3.5 | Preliminary Quantities and Cost Estimate | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
3.6 | VTA QA Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
3.7 | VTA Quality Control (VTAQC) Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
3.8 | Submittals (Printing Only) | N/A
| Sub Total: TASK 3 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 4. FINAL DESIGN – UNCHECKED (65% PS&E)
4.1 | Design Plan Sheets | HRS | 0 | [31 empty] | 0
4.2 | Design Specifications and Special Provisions | HRS | 0 | [31 empty] | 0
4.3 | Design Reports | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
4.4 | Lane Closure Memo | N/A
4.5 | High-Low Risk Utility Certification | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
4.6 | Construction Quantities and Cost Estimate | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
4.7 | Quality Control Process | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
4.8 | VTA QA Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
4.9 | Comment Resolution | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
4.1 | PS&E Submittals (Printing Only) | N/A
| Sub Total: TASK 4 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 5. FINAL DESIGN - CHECKED (95% PS&E)
5.1 | Design Plan Sheets | HRS | 0 | [31 empty] | 0
5.2 | Specifications and Special Provisions (SSP) | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [7 empty] | 0
5.3 | Corrected Final Design Reports | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
5.4 | Right-of-Way and Utility Certification | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
5.5 | Construction Quantities and Cost Estimate | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
5.6 | Construction Schedule | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
5.7 | VTA Quality Assurance (VTAQA) Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
5.8 | VTA Quality Control (VTAQC) Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
5.9 | Joint Resolution Team (JRT) Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
Contractor will perform an independent check of all drawings and calculations per Caltrans Standard procedure for external review of structures PS&E package. Contractor will prepare independent quantity calculations and review the special provisions independently.
Task 4 Deliverables
• Design plan sheets
• Specifications and Special Provisions
• Permit applications and permits
• Right-of-Way certification documents
• Quantity estimate
• Cost estimate
• Cost certification
• Design calculations
• Quantity calculations
• GDMR
• ADL report
• Foundation report
• Caltrans Certification for Compliance with ADA Standards
• Tunnel Safety Forms (Request for Undergrounding)
• Crumb Rubber Usage Report
• Independent structural check calculations
• Independent quantity check calculations
• Final Informational Handout
| Sub Total: TASK 5 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 6. FINAL DESIGN - (100% PS&E) and (Final PS&E)
6.1 | Submittal Plans | HRS | 0 | [31 empty] | 0
6.2 | Permits | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.3 | High-Low Risk Utility Certification | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.4 | Design Report | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.5 | Construction Bid Documents | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.6 | Combining Highways and Structures PS&E Documents | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.7 | Resident Engineer's File | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.8 | QC Process | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.9 | VTA Quality Assurance (VTAQA) Meeting | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.1 | Comment Resolution | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
6.11 | Estimates | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
| Sub Total: TASK 6 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 7. CONSTRUCTION BIDDING SERVICES
7.1 | Bid Documents | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
7.2 | Residnet Engineer File | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
7.3 | Caltrans Construction Encroachment Permit | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
7.4 | Submittals (Printing Only) | N/A
| Sub Total: TASK 7 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 8. DESIGN SERVICES DURING CONSTRUCTION (Amendment)
8.1 | Bid Support Service | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
8.2 | The types of services listed "in-scope services" by Contractor | HRS | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  | 0
| Sub Total: TASK 8 | HRS | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TASK 9. DESIGN SERVICES DURING CONSTRUCTION (Amendment)
ODC PA/ED
| CADD, Plotting, Reproduction (Plans, Reports, and Minutes), Fed Ex, Local Travel | LS | 1 | 5000
| Sub Total |  |  | #REF!
| TOTAL: PLANS, SPECIFICATIONS, & ESTIMATES (PS&E) PHASE | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PSE
Project: Mathilda Ave Landscaping Project
SUBJECT: Form 10 RESOURCE PLAN (stated in percentage only)
ID CODE Letter | Sheet Name | Number of Sheets | Number of Hours/Sheet | Total Hours
TASK 3. PRELIMINARY DESIGN - (35% PS&E)
-- | Title Sheet |  |  | 0
K | Key Map and Line Index |  |  | 0
ISS | Irrigation Sprinkler Schedule |  |  | 0
PL | Plant List |  |  | 0
PP | Planting Plan |  |  | 0
| TOTAL |  |  | 0
TASK 4. FINAL DESIGN – UNCHECKED (65% PS&E)
-- | Title Sheet |  |  | 0
X | Typical Cross Sections |  |  | 0
K | Key Map and Line Index |  |  | 0
WPC | Temporary Water Pollution Control |  |  | 0
WPCD | Temporary Water Pollution Control Details |  |  | 0
EC | Erosion Control |  |  | 0
ECD | Erosion Control Details |  |  | 0
CS | Construction Area Signs |  |  | 0
ISS | Irrigation Sprinkler Schedule |  |  | 0
IP | Irrigation Plan |  |  | 0
ID | Irrigations Details |  |  | 0
IQ | Irrigation Quantities |  |  | 0
PL | Plant List |  |  | 0
PP | Planting Plan |  |  | 0
PD | Planting Details |  |  | 0
E | Electrical Index and Notes |  |  | 0
E | Electric Service (Irrigation) |  |  | 0
| TOTAL | 0 |  | 0
TASK 5. FINAL DESIGN - CHECKED (95% PS&E)
-- | Title Sheet |  |  | 0
X | Typical Cross Sections |  |  | 0
K | Key Map and Line Index |  |  | 0
WPC | Temporary Water Pollution Control |  |  | 0
WPCD | Temporary Water Pollution Control Details |  |  | 0
EC | Erosion Control |  |  | 0
ECD | Erosion Control Details |  |  | 0
CS | Construction Area Signs |  |  | 0
ISS | Irrigation Sprinkler Schedule |  |  | 0
IP | Irrigation Plan
ID | Irrigations Details |  |  | 0
IQ | Irrigation Quantities |  |  | 0
PL | Plant List |  |  | 0
PP | Planting Plan |  |  | 0
PD | Planting Details |  |  | 0
E | Electrical Index and Notes |  |  | 0
E | Electric Service (Irrigation) |  |  | 0
| TOTAL | 0 |  | 0
TASK 6. FINAL DESIGN - (100% PS&E) and (Final PS&E)
-- | Title Sheet |  |  | 0
X | Typical Cross Sections |  |  | 0
K | Key Map and Line Index |  |  | 0
WPC | Temporary Water Pollution Control |  |  | 0
WPCD | Temporary Water Pollution Control Details |  |  | 0
EC | Erosion Control |  |  | 0
ECD | Erosion Control Details |  |  | 0
CS | Construction Area Signs |  |  | 0
ISS | Irrigation Sprinkler Schedule |  |  | 0
IP | Irrigation Plan
ID | Irrigations Details |  |  | 0
IQ | Irrigation Quantities |  |  | 0
PL | Plant List |  |  | 0
PP | Planting Plan |  |  | 0
PD | Planting Details |  |  | 0
E | Electrical Index and Notes |  |  | 0
E | Electric Service (Irrigation) |  |  | 0
| TOTAL | 0 |  | 0
| TOTAL: HIGHWAY DESIGN PLANS |  |  | 0
| TOTAL |  |  | 0
Note on A24: Hernandez, Isaias:
Note on A43: Hernandez, Isaias:
Note on A63: Hernandez, Isaias: