## Form 10 (Hours) - Without Cost
Project: SR 85 Noise Reduction Program Phase 2 (P-0903)
Contract No.: TBD
SUBJECT: Form 10 (Hours) - Resource Plan Without Cost
|  |  |  | PRIME DESIGN CONSULTANTS | [8 empty] | Survey Services |  |  | Environmental Services |  |  |  |  | Traffic Engineering Services |  |  |  |  | Other Services |  |  |  |  | GRAND | GRAND
Item No. | Description | UNIT | Total Time | Principal - in Charge | Project Manager | Deputy Project Manager | Project Engineer | Associate Engineer | Assistant Engineer | Sr. Design & Tech | CADD Admin | TOTAL HRS | Surveyor | Survey Crew | TOTAL HRS | Project Manager | Project Engineer | Associate Engineer | Sr. Design & Tech | TOTAL HRS | Project Manager | Project Engineer | Associate Engineer | Sr Design & Tech | TOTAL HRS | Project Manager | Project Engineer | Associate Engineer | Sr Design & Tech | TOTAL HRS | TOTAL HRS | TOTAL AMOUNT
Task 1: Project Management
| 1.1 Project Administration/Project Coordination | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 1.2 Project Management and Control | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 1.3 Meeting Preparation and Attendance | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 1.4 Develop & Maintain a Quality Management Plan (QMP) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
Sub Total - Task 1 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Task 2: Project Initiation Document (PID)
| 2.1 Preliminary Environmental Analysis Report (PEAR) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 2.2 District Preliminary Geotechnical Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 2.3 Storm Water Data Report (PID Level) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 2.4 Site Visits, Data Collection and Review | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 2.5 Preliminary Plans | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 2.6 Preliminary Right-of-way and Utility Information | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 2.7 Cost Estimate (PID Level) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
| 2.8 Draft and Final PSR/PDS including Supporting Documentation | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | #REF!
Sub Total - Task 2 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Task 3: Project Approval/Environmental Document (PA/ED)
| 3.1 Mapping and Control Surveys | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.2 Right-of-Way Requirements | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.3 Utility Coordination / Utility Policy Certification | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.4 Preliminary Plans | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.5 Traffic Management Plan Data Sheet | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.6 Storm Water Data Report (PA/ED Level) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.7 Draft and Final Preliminary Geotechnical Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.8 Preliminary Construction Cost Estimate and Schedule | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.9 Draft and Final Design Standard Decision Document | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.10 Draft and Final Project Report and supporting documentation | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
3.11 Environmental Document
| 3.11.1 Provide Support for CEQA Environmental Document | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3.11.2 Provide Support for Environmental Special Studies | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 3 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 4: Final Design - (35% PS&E)
4.1 Highway Plan Sheets
| 4.1.1 Title Sheet, Key Map and Line Index | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.2 Typical Cross Sections | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.3 Layout | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.4 Pavement Elevation Sheets | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.5 Drainage Layouts | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.6 Utility Plans | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.7 Stage Construction Plans | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.8 Pavement Delineation | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.9 Summary of Quantities | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.10 Soundwall Modifications - General Plan | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.1.11 Other Pertinent Plans | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.2 Structure Type Selection - Soundwall Modification Design | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.3 Cost Estimate and Specification Outline | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
4.4 Right-of-Way Engineering
| 4.4.1 RW Needs, Data Sheet and Certification | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.4.2 RW Surveying, Mapping and Documentation | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.5 Utility Design Process | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.6 Utility Coordination Responsibility | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.7 Update Design Survey | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 4.8 VTA Quality Assurance/Quality Control Audit Meeting | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 4 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 5: Final Design - (65% PS&E) |  | HRS
| 5.1 Design Plan Sheets | HRS
| 5.1.1 Highway Design Plans | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.1.2 Structure Plan Sheets | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.2 Project Specifications and Standard Special Provisions | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.3 Right-of-Way and Utility Certifications | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.4 Construction Quantities and Cost Estimate | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.5 Combining Highway and Structures PS&E Documents | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.6 VTA Quality Assurance Meeting | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.7 Joint Resolution Team Meeting | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 5.8 PS&E Documentation | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 5 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 6: Final Design Reports
| 6.1 Geotechnical Design Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.2 Foundation Report and Log of Test Borings | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.3 Pavement Design and Materials Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.4 Sight Investigation Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.5 Drainage Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.6 Stormwater Data Report and BMP Checklist | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.7 Lane Closure Report | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.8 Transportation Management Plan | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.9 Utility Policy Variance Request | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.10 Supplemental Design Standard Decision Document | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 6.11 Supplemental Traffic Analysis (Allowance) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 6 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 7: Final Design - 95% PS&E
| 7.1 Design Plan Sheets | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.2 Project Specifications and Special Provisions | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.3 Draft Permits | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.4 Right of Way and Utility Certification | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.5 Construction Quantities and Cost Estimate | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.6 Construction Schedule | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.7. VTA Quality Assurance Meeting | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.8 Joint Resolution Team (JRT) Meeting | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.9 Biddability Meeting | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 7.10 Independent Check (Structures) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 7 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 8: Final Design - 100% PS&E and Final PS&E
| 8.1 Plans, Specifications and Estimate | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.2 Final Permits | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.3 Right-of-Way and Utility Certification | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.4 Construction Bid Documents | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.5 Resident's Engineer File and Survey File | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.6 VTA Quality Assurance Meeting (2 Meetings) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.7 JRT Meeting (2 meetings) | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 8.8 Noise Study Report - Before and After | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 8 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 9: Construction Bidding Services
| 9.1 Bid Document Revisions | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 9.2 Bid Addenda | HRS | 0 | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub Total - Task 9 |  | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRODUCTIONS OF MILESTONE DELIVERABLES/DOCUMENT MANAGEMENT
| CADD, Plotting, Reproduction (Plans, Reports, and Minutes), Fed Ex, Local Travel | LS | 1
Sub Total - ODC |  | HRS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GRAND TOTAL | HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Note: Add additional rows and columns as necessary